Bharat Sanchar Nigam Limited

Corporate Office

Bharat Sanchar Bhavan

New Delhi-110001

S R KAPOOR

EXECUTIVE DIRECTOR (FINANCE)

D.O. No.   EDF/ Kuber/ TR  /BSNL

12th June, 2009

Subject: National roll out of “Collections Initiative” of  Project Kuber (Revenue Assurance project)

Dear Shri

As part of Project Shikhar, we along with the help of BCG had launched a project on revenue assurance, aptly named “Kuber”. A pilot of the project was launched in Pune SSA to detail out the design and learn from on the ground implementation.  In the last two months since the launch, the pilot has been very successful, already resulting in achievement of ~30% of target.

We are now rolling out the project nationally. This letter will provide you with an overview of the Collection Initiative of Project Kuber along with a set of activities that have to be carried out by you immediately, to enable a successful national roll out.

Overview of Project Kuber:

Revenue Assurance is the process of assessing and preventing revenue leakages across the billing value chain, including the processes of measurement, billing and collection. Through a process of opportunity identification and prioritization, two initiatives were identified for immediate roll out:

- Collection of Bad Debt

- Leased Circuits Billing

The following sections will focus on “Collection of bad Debt”

Collections: As on 31st March 2008, BSNL had cumulative bad debts (outstanding grater than 3 months old) of Rs. 4399 crores. Of the Rs. 4399 crores, 1411 crores of bad debt is less than 2 years old.  The Collections initiative will focus on recovery of these bad debts through a segmented approach, appointment of external bad debt collection agencies and increasing efficiency of internal BSNL team.

In the pilot held in Pune, the following activities were conducted:

  - Segmentation of bad debt on the basis of age, account size and geography

  - Assessment and appointment of collection agencies

  - Setting up internal teams and processes for support, monitoring and review

  - Creation of internal team for collection of large value accounts

Over Rs. 60 lacs of bad debt has been recovered by the initiative so far in Pune. Based on the activities being carried out in Pune, we estimate that there is an overall potential of Rs. 250 – 300 Crore from the initiative on bad debt collections.

Key Activities

This section describes in detail the set of activities that need to be conducted as part of the Collections Initiative.

Collections

- Data collection and analysis

  - Collection of account wise data on bad debt for Basic Services, CMTS and Leased circuits

  - Segmentation of data based on age, geography and account size

- Appointment of external collection agencies

  - Detailed assessment of collection agencies operating in the SSA

  - Appointment of agencies and signing of contracts

- Creation of internal team for collection of large value outstanding

- Creation of support, monitoring and review processes

  - Setting up support and monitoring team at each SSA

  - Setting up system for analysis, links to CSMS etc.

Team required for the project

To realize the above mentioned potential, we are launching a national roll out of the Collections Initiative of Project Kuber immediately.  The program will be conducted by teams at three levels: Head Office (HO), Circle Office (CO) and SSA. Description of the team required at Circle Office (CO) and SSA are given below.

| S.No. | Position | Required Designation | Circle / SSA | Full Time / Part Time | Role |
| --- | --- | --- | --- | --- | --- |
| 1 | Circle Head - Collections | GM (Finance) / DGM (Finance) | Cicle | Part Time | Overall head of project; responsible for delivery |
| 2 | Project Manager Circle - Collections | DGM / CAO | Cicle | Full Time | Manage project at Circle level; Ensure delivery of milestones for all SSAs |
| 3 | Project Manager SSA - Collections | IFA | SSA | Part Time | Responsible for execution of project at SSA level |

The Project Manager at the Circle level may appoint support staff as required for tracking the activities at the SSA level.

The Project Manager at the SSA level will appoint and manage team for executing on-ground activities. The details of the team required will be provided during training sessions to be held in June.

Action Items

To have a successful roll out we need your whole hearted support and cooperation.  As a first step, we need to identify the team at the CO and SSA level as per the previous section.

I would request you to quickly identify the teams for your Circle (based on the table given above) – Both at the Circle office level and the SSA levels and submit to Mr. Deepak Agrawal, DGM (Restructuring I) at Head Office (HO) by 19th June. A format for the nominations is attached.

A comprehensive training will be conducted for the identified people that will cover in detail the entire set of activities for the project.

Project Kuber is a major initiative that has the potential to recover significant amounts of money, and is the first step in ensuring tighter controls in the future. I am counting on your wholehearted support to make this project a grand success.

With warm regards,

Yours sincerely,

-sd/-

(S R Kapoor)

To

All CGMs Territorial Circles, BSNL.

Format for Nominations for Project Kuber - Collections

| Circle |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Circle Level Nominations |  |  |  |  |  |
|  | Initiative | Position | Name | Designation | Mobile No. |  |
|  | Collections | Circle Head - Collections |  |  |  |  |
|  |  | Project Manager Circle - Collections |  |  |  |  |
| SSA Level Nominations |  | Project Manager SSA - Collections |  |  |
|  | S. No. | SSA | Name | Designation | Mobile No. |

Note: Please submit this completed format by 15th June to Mr. Deepak Agrawal, DGM (Restructuring I) at HO.

Email: deepak.agrawal0@gmail.com, Fax: 011 - 23734353, Mobile: 9868218081